## Sheet1
Tasks and Assignment Breakdown
| Group: | Group 5
| Team Members (and initials): | Daniel Beeman (DB), Holly Hardin (HH), Linshu Huang (LH), Maxwell Logan (ML), Yiming Ni (YN)
| Date this was last updated: | 2019-02-02
| Last updated by (whom): | ML
In general, you should archive a copy of this spreadsheet (with the date in the file name) before modifying it.
(The tasks can be grouped by week, major activity or other. You can delete this row from the spreadsheet.)
Grouping | Task or Milestone (with an objectively verifiable completion) | Status | Assigned to (whom) | Date Assigned | Date Due | Date Completed | Completed by (whom) | Confirmed Completed by (whom) | Date Confirmed Complete | Notes
Week 1
| Establish weekly meeting schedule. Post on shared repository. | completed | all staff | 2019-01-09 | 2019-01-09 | 2019-01-09 | all staff | all staff | 2019-01-09
| Group meeting | completed | all staff | 2019-01-12 | 2019-01-12 | 2019-01-12 | all staff | all staff | 2019-01-12 | Max attended via Discord
Week 2
| Generate v1 of Initial project plan / SRS / SDS and post on shared repository | completed | HH, DB | 2019-01-09 | 2019-01-17 | 2019-01-17 | HH, DB | HH,DB | 2019-01-17
| Group meeting | completed | all staff | 2019-01-14 | 2019-01-14 | 2019-01-14 | all staff | all staff | 2019-01-14
| Write up summary of client meeting. Post on shared repository. | completed | DB | 2019-01-18 | 2019-01-18 | 2019-01-18 | DB | DB | 2019-01-18
| Have initial meeting with client to review v1 of IPP / SRS / SDS | completed | all staff | 2019-01-18 | 2019-01-18 | 2019-01-18 | all staff | all staff | 2019-01-18
| Generate the dynamci and static module | completed | HH, DB | 2019-01-15 | 2019-01-17 | 2019-01-17 | HH, DB | HH,DB | 2019-01-17
Week 3
| Generate v2 of Initial project plan / SRS / SDS and post on shared repository | completed | DB, ML, YN | 2019-01-18 | 2019-01-23 | 2019-01-23 | DB, ML, YN | DB,ML,YN | 2019-01-23
| Milestone L0 - Display Calendar | completed | HH, DB | 2019-01-14 | 2019-01-22 | 2019-01-22 | HH, DB | HH,DB | 2019-01-22
| Milestone L0 - Add Event | completed | HH, YN | 2019-01-14 | 2019-01-25 | 2019-01-23 | HH, YN | HH,YN | 2019-01-25
| Group meeting | completed | all staff | 2019-01-12 | 2019-01-22 | 2019-01-22 | all staff | all staff | 2019-01-22
| Have meeting with client to review progress of project | completed | all staff | 2019-01-24 | 2019-01-25 | 2019-01-25 | all staff | all staff | 2019-01-25
Week 4
| Milestone L0 - Display Event | completed | HH, LH, DB | 2019-01-14 | 2019-01-27 | 2019-01-24 | HH [LH, DB] | HH | 2019-01-24
| Performance Review | completed | HH | 2019-01-14 | 2019-01-27 | 2019-01-26 | HH | HH | 2019-01-26
| Milestone L1 - Save Data to Database | completed | HH, DB, LH, YN | 2019-01-14 | 2019-01-27 | 2019-01-31 | HH, DB | HH, DB | 2019-01-31
| Milestone L1 - Add/Edit/Delete Event | completed | HH, DB, LH, YN | 2019-01-14 | 2019-01-27 | 2019-01-31 | HH, DB, LH, YN | HH, DB, LH YN | 2019-01-31
| Milestone L1 - Display Event | completed | HH, DB, LH, YN | 2019-01-14 | 2019-01-27 | 2019-01-26 | HH | HH | 2019-01-26
| Milestone L1 - Work for all days in 2018-2020 | completed | HH, DB, YN | 2019-01-14 | 2019-01-27 | 2019-01-25 | HH | HH | 2019-01-25
| Group Meeting | completed | all staff | 2019-01-28 | 2019-01-28 | 2019-01-28 | all staff | all staff | 2019-01-30
| Group Meeting | completed | all staff | 2019-01-29 | 2019-01-29 | 2019-01-29 | all staff | all staff | 2019-01-30
Week 5
| Add Categories | completed | LH | 2019-01-29 | 2019-02-01 | 2019-02-01 | all staff | ML | 2019-02-01
| Add Priorities | completed | LH | 2019-01-29 | 2019-02-01 | 2019-02-01 | all staff | ML | 2019-02-01
| Update Technical Documentation | completed | ML | 2019-01-28 | 2019-01-30 | 2019-02-01 | ML | ML | 2019-02-01
| Update User Documentation | completed | ML | 2019-01-28 | 2019-01-31 | 2019-01-31 | ML | ML | 2019-01-31
| Performance Review | completed | ML | 2019-01-14 | 2019-02-01 | 2019-01-31 | ML | ML | 2019-01-31
| Team Meeting | completed | all staff | 2019-01-14 | 2019-02-02 | 2019-02-02 | all staff | all staff | 2019-02-02
| Unit Testing | completed | all staff | 2019-01-14 | 2019-02-05 | 2019-02-05 | YN | ML | 2019-02-05
| Assemble Presentation | completed | ML | 2019-01-28 | 2019-02-05 | 2019-02-02 | ML | ML | 2019-02-02
| Team Meeting | completed | all staff | 2019-02-05 | 2019-02-05 | 2019-02-05 | all staff | all staff | 2019-02-05
| Present Project | not completed | all staff | 2019-02-06 | 2019-02-06